## Time-phased
| Activities per Month | Budgeted Monthly Cost
|  | March | April | May | June | July | August | September | October | November | December | totals
1 | Initiation | 548640 | 594360 | [8 empty] | 1143000
2 | Requirement Gathering & Analysis |  | 406510 | 282490 | [7 empty] | 689000
3 | Design |  |  | 372750 | 670950 | 447300 | [5 empty] | 1491000
4 | Development and Integration |  |  |  | 139560 | 93040 |  |  | 465200 | 465200 |  | 1163000
5 | Programming challenges and competition |  |  |  |  | 50760 | 33840 |  |  | 169200 | 169200 | 423000
6 | Collaboration and project management tools |  |  | 44220 | 29480 |  | 73700 | 73700 | 73700 |  | 73700 | 368500
7 | Testing and quality assurance |  |  |  | 178100 | 356200 | 89050 | 89050 | 356200 | 356200 | 356200 | 1781000
8 | Deployment and Launch | [7 empty] | 207600 | 233550 | 77850 | 519000
9 | Closure Phase | [8 empty] | 578500 | 311500 | 890000
10 | maintainance and support | [7 empty] | 136500 | 136500 | 182000 | 455000
Software
| Software Deployment (annualy) - License | [7 empty] | 9900 | 9900 | 10200 | 30000
Procurement
| blood testing and screening device | 100000 | [9 empty] | 100000
Overhead Cost
| 30% of development cost |  |  |  | 41868 | 27912 |  |  |  | 139560 | 139560 | 348900
Reserves
| 20% of all estimate | 129728 | 200174 | 139892 | 211991.6 | 195042.4 | 39318 | 32550 | 249820 | 417722 | 264042 | 1880280
| Totals | 778368 | 1201044 | 839352 | 1271949.6 | 1170254.4 | 235908 | 195300 | 1498920 | 2506332 | 1584252 | 11281680

## Cost-Estimation-phased
Work Breakdown Structure | Project Manager | Business Analyst | Software Engineer1 | Software Engineer2 | Software Engineer3 | Tester1 | Tester2 | Tester3 | Tester4 | UI/UX designer | Database Analyst | Technical Writer | Information Security Analyst | Front-end Developer | Devops Engineer | Back-end Developer | Software Analyst | Risk analyst | Total | %age of Salary Cost
Initiation | 62 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1143000 | 12.81%
Requirement Gathering & Analysis | 15 | 47 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 689000 | 7.722%
Design | 12 | 10 | 23 | 23 | 23 | 0 | 0 | 0 | 0 | 32 | 34 | 9 | 8 | 22 | 0 | 0 | 7 | 12 | 1491000 | 16.71%
Development and Integration | 8 | 0 | 18 | 18 | 18 | 15 | 15 | 15 | 15 | 4 | 0 | 11 | 0 | 6 | 4 | 6 | 8 | 0 | 1163000 | 13.03%
Programming challenges and competition | 4 | 0 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 2 | 0 | 3 | 0 | 3 | 1 | 1 | 3 | 0 | 423000 | 4.741%
Collaboration and project management tools | 2 | 0 | 10 | 10 | 10 | 2 | 2 | 2 | 2 | 1 | 0 | 5 | 0 | 2 | 1 | 1 | 2 | 0 | 368500 | 4.13%
Testing and quality assurance | 0 | 0 | 8 | 8 | 8 | 52 | 52 | 52 | 52 | 3 | 0 | 5 | 3 | 4 | 0 | 4 | 0 | 6 | 1781000 | 19.96%
Deployment and Launch | 4 | 0 | 7 | 7 | 7 | 2 | 2 | 2 | 2 | 0 | 0 | 3 | 29 | 0 | 8 | 0 | 8 | 0 | 519000 | 5.817%
Closure Phase | 14 | 3 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 3 | 6 | 3 | 7 | 7 | 7 | 7 | 3 | 890000 | 9.975%
maintainance and support | 12 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 455000 | 5.099%
Totals # of days worked | 133 | 75 | 91 | 91 | 91 | 87 | 87 | 87 | 87 | 49 | 37 | 42 | 43 | 44 | 21 | 19 | 45 | 39
per day salary of employee ( pkr ) | 15000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 5000 | 5000 | 5000 | 7500 | 6000 | 7500 | 6000 | 6000
Total salary according to work-days | 1995000 | 525000 | 637000 | 637000 | 637000 | 609000 | 609000 | 609000 | 609000 | 343000 | 185000 | 210000 | 215000 | 330000 | 126000 | 142500 | 270000 | 234000 | 8922500
Software
Softwarer Deployment (annualy) | 30000
Procurement
blood testing and screening device | 100000
Overhead Cost
30% of development cost | 348900
Reserves
20% of all estimate | 1880280
Budgeted Cost of Work Scheduled (BCWS) | 11281680